## Sheet1
Risk number | Risk Assigned to (Name of the Group member) | Risk title | Risk description | Likelihood Score | Likelihood Score justification | Impact Score | Impact Score justification | Risk value | Risk Score/rank (impact * Likelihood) | General Notes / Review comments | Software / Hardware Solutions (Q8)
1 |  | Dependency on third-party AI and data APIs (V2) | V2's AeroAI Advisor and live enrichment (visa, currency, weather) depend on external AI and data APIs. These can rate-limit, slow down, return errors, or go offline, and API keys carry cost. | 4 | External API rate limits and transient outages are common and likely to surface during heavy use or a live demo. | 4 | If unhandled, the advisory layer (the project's smart differentiator) breaks and can stall the workflow. | 4x4 | 16 |  | Software: response caching; automatic fallback to V1's deterministic ranking when an API is unavailable; request timeouts with retry and backoff; clear degraded-mode messaging; quota and key-usage monitoring. Infrastructure: runs client-side, so no servers are required; keep the API key off the client via a thin proxy if cost or abuse is a concern.
2 |  | Manifest V3 / Chrome extension API changes | Chrome periodically changes or deprecates extension APIs under Manifest V3, and a change can break loading or core functionality. | 3 | Chrome ships frequent updates, so an API change affecting the extension within the project timeline is plausible but not constant. | 4 | Could stop the extension from loading or disable a feature, blocking use until patched. | 3x4 | 12 |  | Software: target stable documented MV3 APIs; avoid deprecated calls; feature-detect and degrade gracefully; track Chrome release notes; run a regression test suite against each Chrome update.
3 |  | Unreliable or hallucinated AI recommendations | The AI advisor can return confidently wrong or fabricated assessments (for example overlooking a visa requirement), because AI outputs have no single checkable correct answer (the oracle problem). | 4 | LLM-based components are known to produce plausible but incorrect outputs; without guardrails this is likely. | 4 | Bad layover advice misleads a traveler on real decisions such as visa or feasibility, damaging trust and usefulness. | 4x4 | 16 |  | Software: constrain prompts and parse and validate AI output against deterministic checks (visa, season, layover length); never let the AI override hard constraints; show the V1 deterministic score alongside the AI verdict; apply robustness and metamorphic-style testing to the advisor (cf. Zhang et al., 2022).
4 |  | Inaccurate offline data or scoring approximation | The local airport and geocoding database can go stale, stopover-program data can change, and the Haversine great-circle distance underestimates real routed travel time. | 3 | Static data drifts over time and great-circle distance is a known approximation, so misranking is possible though not guaranteed for every query. | 3 | Produces misranked or outdated routes, which weakens trust, but it is not safety-critical. | 3x3 | 9 |  | Software: version and date-stamp the local database with a scheduled refresh; unit-test the scoring and Haversine engine; label distances as estimates; validate stopover-program data against a source on each update.
5 |  | Extension security and permission or data exposure | As a browser extension, LayoverNow is exposed to permission over-reach and data-leak risks common to the extension ecosystem (cf. Obimbo et al., 2018). | 3 | Extensions are a frequent target for permission abuse and data leakage; the risk is real but manageable with good practices. | 4 | Over-broad permissions or leaked trip data would be a privacy and security failure and could cause Web Store rejection. | 3x4 | 12 |  | Software: follow least privilege and request only needed permissions; keep V1 search fully offline; use HTTPS only for V2 calls; store no sensitive personal data; apply a Content Security Policy; sanitize all inputs; review the permission set before each release.